# Measuring change in the K&S system — Week 9 method note

How to get a defensible baseline out of the Kendry & Slate practice-management data using Rose’s ks_* tools. This note gives you the method, not the answers. The numbers are deliberately not printed here — a case for change that someone handed you is not a case for change you can defend under questioning.

## The tools

| Tool | What it gives you | Use it for |
| --- | --- | --- |
| ks_list_matters | Every matter you can see, with status, fee type and total fees | Orientation; finding your matter id |
| ks_get_matter | One matter with its task plan, estimated and actual hours, dates and team | Plan-versus-actual; overdue analysis |
| ks_list_tasks | Tasks filtered by status, workstream or phase | Where the plan is failing, and in which phase |
| ks_time_ledger | Time entries with source and operator_name | The most important one. How time was captured, and by whom |
| ks_list_staff | Fee earners with charge-out and cost rates | Converting hours into dollars |
| ks_record_time_entry | Writes a time entry (approval-gated) | Only where an exercise calls for it |

You can see your own group’s matter plus the shared NexaCare matter. That is the scope by design; it is also a constraint on your comparisons, and you should say so in your plan rather than write around it.

## Six baselines worth having

Ask Rose for each of these. Record the figure, the date you took it, and the tool call that produced it — the measurement appendix in your change pack is that list.

- Plan-versus-actual on the matter. Total estimated hours in the task plan against total hours ever recorded. The ratio is the headline number of your case for change, and it will do more work than any adjective.

- Task completion. How many tasks are complete, and how many are past their due date. Report both. One without the other is arguable.

- Coverage. How many tasks carry zero recorded time. This distinguishes “we are behind” from “we are not tracking”, which are different problems with different fixes.

- Capture method. The time ledger by source. Contemporaneous entries versus entries created by adjustment or sync. This is the sharpest number available to you, because it speaks to whether the record can be relied on at all.

- Concentration. Recorded hours by person and by rate. Who is actually carrying the matter, and what does that cost per hour?

- Cost of the gap. Unrecorded planned hours × the relevant charge-out rate. Treat this as an exposure figure, not a loss — and say which it is.

## Three traps

The zero-is-good trap. A low recorded-hours figure can mean the work has not been done, or that it has been done and not recorded. Those imply opposite interventions. Distinguish them with a second query before you build an argument on either.

The precision trap. “$186,000 of unrecorded exposure” invites an argument about the $6,000. “Roughly a quarter of a million dollars of planned work with no time against it” does not. Match the precision of the claim to the precision of the evidence.

The seeded-data trap. This is a teaching database. Some figures are extreme because they were built to be. Say what you are assuming: that the pattern is real even where the magnitude is illustrative. An examiner respects a stated assumption and marks down a hidden one.

## What good looks like

Every number in your change pack should carry, in a footnote or an appendix line, the tool call that produced it and the date. Any figure that does not is an assertion, and a partnership audience will treat it as one.

If a claim cannot be measured with data the firm actually captures, that is itself a finding — write it down as a measurement gap rather than deleting the claim.