# Week 9 — Transformation and Change Management

One hour. Five activities. Work in your group.

Everything you need is in the Library folder Week 9 — Change management. Read 04-nexacare-change-brief.docx first — it sets the scenario.

## The scenario, in short

Your Week-8 client happy path has been approved as a 90-day pilot on the NexaCare matter. Four behavioural asks of the team: record time contemporaneously, keep task status in the system, hold defined client touchpoints, and make the matter plan visible. No new software — everything is already possible in K&S today.

Every one of those is individually trivial. Together they change what a lawyer’s Tuesday looks like, they make individual working patterns visible for the first time, and they cost time that is not billable.

## Before you start

Open Workflows and filter for (W9) — exactly five.

You have read access to the K&S data for your own matter and for NexaCare. Use it. 03-measuring-change.docx tells you how to pull a baseline; it deliberately does not tell you what you will find.

## The five activities

### 1. Change urgency — the evidence · ~12 min

Find out what is actually true about the NexaCare matter, from the data, before you argue anything. Plan versus actual, task completion, how time was captured.

Then score D × V × F > R — dissatisfaction, vision, first steps, resistance. It is a product, not a sum: if any term is zero, nothing happens.

Expect this to be uncomfortable. That is the point.

### 2. Guiding coalition & diffusion map · ~10 min

Who leads the change, and — harder — who do you approach first? Place the personas on Rogers’ adopter curve and test your coalition against Kotter’s four requirements: position power, expertise, credibility, leadership.

The intuitive answer is “start with the enthusiasts”. It is usually wrong.

### 3. Change impact assessment · ~12 min · tabular

One row per persona, ten columns. Attach the seven persona documents as rows.

Two columns do the real work: what they lose, and the adoption signal. If your assessment says someone loses nothing, you have not looked hard enough. People resist loss, not change.

### 4. Quick wins — 90 day plan · ~11 min

Three wins, each visible, measurable against a baseline you captured, and deliverable inside 90 days. Kotter’s distinction matters: short-term wins are created, not hoped for.

Include the anti-victory line — what you will say when the first win lands, so nobody declares the change finished.

### 5. Week 9 change pack · ~15 min

Assemble and export. Build the golden-thread table: every intervention traced to a documented problem, every problem to an intervention or an explicit decision not to act.

Export the Process report. For a change plan, showing how you reached a position is usually more persuasive than the position.

## The question the week turns on

Every change plan can explain why someone should adopt it.

Why would James Bentley actually do this? Not should. Would.

A plan that can only answer the first question is the plan Kotter wrote his article about.

## A note on the data

This is a teaching database and some figures are extreme by design. Say what you are assuming — that the pattern is real even where the magnitude is illustrative. A stated assumption earns marks; a hidden one loses them.